## peer-review--project-initiation
Item	Score
Was a sponsor appointed to the project from the beginning?	100
Is the sponsor involved in high-level aspects of the project?	60
Does the sponsor avoid getting involved in the detail?	50
Was the project manager appointed to the project from the beginning?	100
Is the project manager familiar enough with P3.express?	50
Is there an effective setup for the project documents?	80
Are there enough key team members appointed to the project?	80
Were key team members actively involved in planning the project?	100
Is the Project Description well formed and useful?	80
Is the Deliverables Map well formed and useful?	80
Is the Follow-Up Register well formed and useful?	80

## peer-review--monthly
Item	w1	w2	w3	w4	w5	w6	w7	…
Was the plan for the upcoming month properly refined?	95%	95%	95%	95%	100%
Is the high-level plan properly revised?	90%	85%	95%	95%	100%
Is customer satisfaction evaluated properly?	100%	95%	100%	100%	100%
Is team satisfaction evaluated properly?	90%	80%	85%	90%	100%
Have we planned effective improvements?	90%	100%	100%	100%	100%
Have we captured lessons learned?	85%	90%	95%	90%	100%
Have we conducted effective focused communications?	80%	85%	90%	90%	100%
Is the performance measurement reliable and useful?	90%	95%	90%	85%
Are the progress reports well formed and useful to their audience?	100%	100%	100%	100%
Have we collected feedback from the reports?	100%	100%	100%	100%
In the case of deviations, is there a proper recovery plan?	90%	95%	95%	90%
In the case of important deviations, was the sponsor involved in planning the response?	0%	0%	0%	0%
Did we have a proper kick-off events?	95%	100%	100%	100%
Did we manage risks, issues, and change requests properly and on a daily basis?	95%	100%	100%	100%
In the case of completed deliverables, have we checked and accepted them properly?	95%	100%	100%	100%

## peer-review--project-closure
Item	Score
Is the product approved and handed over?
In the case of remaining activities, are they clearly listed and approved?
Has customer satisfaction been evaluated and recorded?

## satisfaction--team
Item	Score(Project Manager)	Score(Team Leader)	Score(Developer)	Score(Database Admin)
Did the team member complete their each other given tasks ?	100%	100%	100%	100%
Did the team accecpt the accomplishment of the project ?	100%	100%	100%	100%
Did the team had the hard times during development and solves those problems ?	80%	70%	90%	60%
Did the team manage their time on each tasks perfectly?	95%	90%	100%	90%
Did the team complete their works on each deadlines?	95%	95%	100%	90%
Did the team have a good communiation with each other?	100%	100%	100%	100%
Did team face too many risks during the developement ?	70%	60%	90%	60%
Did the client enjoy about the efforts of the team?	90%	90%	95%	85%
Did the team have great meeting times?	100%	100%	100%	100%

## satisfaction--customer
Item	Score
Did the client had the development process that she desired?
Did the client accept the current stage of the developement?
Did the client and team had the good relationship about this project?
Client has the general issues about the development?
How much rating for this development?

## PeerReview
Questions	Score	Feedback
Is the deliverable map acceptable or not?
Do the risks that are included in the follow-up register cover for the whole project?
How do you think of our teamwork skill according to the quality of the work?
Does the expected outcome(goal) match the final result?
Do you like to use this system if you were a client?
Is the developed system useful in the real life?
Do you like the UI of the developed system?
Do the system performace work well?
Does the system have required functions compare with the other system?
Score

Do you want to point out any suggestions for our team?
Answer Here